## ProjectSchedule
Dashboard Project Tracker |  |  | Updated: 1:03pm 7/13/2022 by mark
|  |  | Project Start: |  | 2022-07-19
|  |  | Display Week: |  | 1 |  |  |  | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05
 | time axis 2022-07-18 to 2022-09-11
SCOPE | TASK | DESCRIPTION | ASSIGNED TO | PROGRESS | START | END | NOTES | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Dashboard Prototype Version 1 ( July ) * Framework , Metrics , data, UI in PPT for TW and P33 discussion
1. Organization & Framework | Task 1.1 | Road map proposal 1st draft | Mark | 100% | 2022-07-12 | 2022-07-12 |  | 1
| Task 1.2 | 1st Framework Draft Discussion | Mark, Sebastian | 100% | 2022-07-13 | 2022-07-13 |  | 1
| Task 1.3 | Road map proposal 2nd draft on Xmind | Mark | 100% | 2022-07-14 | 2022-07-14 |  | 1
| Task 1.4 | 2nd Framework Draft Discussion | Matthew, Mark, Sebastian | 100% | 2022-07-15 | 2022-07-15
2. Database | Task 2.1 | Collecting spatial data for ethic and geographic disparity analysis | Mark | 100% | 2022-07-12 | 2022-07-19
| Task 2.2 | Data request review | Matthew, Sebastian | 100% | 2022-07-14 | 2022-07-15
| Task 2.3 | Spatial data cleaning | Mark | 0% | 2022-07-20 | 2022-08-05
| Task 2.4 | Data colletion (additional) after metrics setting settled first round | Mark, Sebastian | 100% | 2022-07-13 | 2022-07-29
3. Metrics & Methology | Task 3.1 | 1st Metrics Draft Discussion | Sebastian, Mark | 100% | 2022-07-12 | 2022-07-13
| Task 3.2 | Powerpoint for Matthew | Mark | 100% | 2022-07-13 | 2022-07-14
| Task 3.3 | 2nd Metrics Draft Discussion | Matthew, Mark, Sebastian | 100% | 2022-07-15 | 2022-07-15
| Task 3.4 | Rivision | Mark, Sebastian | 100% | 2022-07-18 | 2022-07-22
4. Visualization strategy | Task 4.1 | Message that matters | Sebastian | 100% | 2022-07-12 | 2022-07-21
| Task 4.2 | Desgin sample on ppt | Mark | 100% | 2022-07-12 | 2022-07-14
| Task 4.3 | Prototype Discussion | Matthew, Mark, Sebastian | 100% | 2022-07-15 | 2022-07-25 |  | 11
5. Prototype Presentation | Task 5.1 | P33 Internal Discussion | P33 Team | 100% | 2022-07-26 | 2022-07-29
6. Prototype Revision and 2nd presentation | Task 6.1 | Methodology adjustments (Geometric avg.) | Sebastian | 100% | 2022-07-26 | 2022-07-29
| Task 6.2 | Presentation Powerpoint | Mark | 100% | 2022-07-27 | 2022-07-29
| Task 6.3 | Discussion with TW | Matthew, Mark, Sebastian | 100% | 2022-08-01 | 2022-08-01 |  | 1
Dashboard Prototype Version 2 ( August )
Weekly meeting | 1st week internal meeting | Aug.1 TW meeting follow-up, p33 team 1st week workload distribution | Matthew, Mark, Sebastian | 100% | 2022-08-02 | 2022-08-02 | 1st week confirmation on timeline and workload distribution | 1
| 1st week external meeting | Confirmation on timeline, math teacher data and workload distribution among TW and P33 | Matthew, Mark, Sebastian | 0% | 2022-08-03 | 2022-08-03 |  | 1
| 2nd week internal meeting | Confirmation on the metrics and methodology | Matthew, Mark, Sebastian | 0% | 2022-08-09 | 2022-08-09 | 2nd week finalize datam methodology and metric designs
| 2nd week internal meeting | Feedback on the metrics and methodology and sharing with TW | Matthew, Mark, Sebastian | 0% | TBD | TBD
| 3rd week internal meeting | Metric Graphs | Matthew, Mark, Sebastian | 0% | 2022-08-16 | 2022-08-16 | 3rd week start pitching graph designs
| 3rd week external meeting | Metric Graphs | Matthew, Mark, Sebastian | 0% | TBD | TBD
| 4th week internal meeting | Metric Graphs and Interactive tools | Matthew, Mark, Sebastian | 0% | 2022-08-23 | 2022-08-23 | 4th week finalize graph designs and start pitching interactive tools
| 4th week external meeting | Metric Graphs and Interactive tools | Matthew, Mark, Sebastian | 0% | TBD | TBD
| 5th week internal meeting | Interactive tools | Matthew, Mark, Sebastian | 0% | 2022-08-30 | 2022-08-30 | 5th week finalize interactive tools
| 5th week internal meeting | Interactive tools | Matthew, Mark, Sebastian | 0% | TBD | TBD
1. Dataset on Excel | Update Shared Dataset | Download and update two csv files on Github | Sebastian | 50% | 2022-08-02 | 2022-08-03 |  | 2
| Data collection | Locattion metrics collection | Sebastian | 30% | 2022-08-02 | 2022-08-08
| Transiton | Transition, data handover | Sebastian | 0% | 2022-08-08 | 2022-08-08
| Data collection | TW math teacher data | Matthew, TW | 0% | 2022-08-02 | 2022-08-09 | no later than Aug.9
2. Dataframe on R | Dataframe construction | Completing R file and Dataframe | Mark | 0% | 2022-08-03 | 2022-08-04 | before 2nd week internal meeting
| Data verification | Update and Cross examniation on Data and Metrics | Mark | 0% | 2022-08-05 | 2022-08-07 | before 2nd week internal meeting
| Data verification | Cross examniation on finalized Data and Metrics | Mark | 0% | 2022-08-08 | 2022-08-10 | before aug.19 Seb left | 3
| Finalize Dataframe | Sharing finalized df with TW and P33 on github | Mark | 0% | 2022-08-11 | 2022-08-11
3. Narratives and Implications | Task 3.1 | Narratives and Story | Matthew | 0% | TBF | TBF | Preferably before the 2nd week meeting
| Task 3.2 | Implications | Matthew | 0% | TBF | TBF | Preferably before the 3rd week meeting
4. Prototype with metirc graphs | produce graph | Producing graphs on R for internal discussion | Mark, Sebastian | 0% | 2022-08-11 | 2022-08-16 | 12 to 20 graphs estimated, 4 - 5 graphs a day,before aug.19 seb leaving | 6
| revise graph | Graph and Prototype revision | Mark, Sebastian | 0% | 2022-08-17 | 2022-08-19 | before 3rd week internal meeting | 3
| produce ppt | Producing Prototype PowerPoint win all graphs attached | Mark | 0% | 2022-08-20 | 2022-08-23 | before 4th week internal meeting
5. Prototype with metric graphs and interactive tools | pitching interactive tools | Prototype ppt for interative tool | Mark, Matthew | 0% | 2022-08-16 | 2022-08-23 | before 4th week internal meeting
| Revise Interactive tools | Interactive tool Revision | Mark | 0% | 2022-08-24 | 2022-08-26 | before 5th week internal meeting
| Final Prototype ppt | Final Prototype ppt | Mark | 0% | 2022-08-29 | 2022-08-31 | By the end of August | 3
Dashboard Prototype go online ( Sep ) * To be planned after 1st week external meeting in August with TW.
Formulas:
TBF = [TBF]+5
TBF = [TBF, row above]+1

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.